## Group member 1
To-do list
To be completed by: |  | 2023-12-08 |  | Name Samin Chowdhury
Deadline: |  | 2023-12-08 |  | Date 12/07/2023
Project 3
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Delegate consturcting tables ¦ 3NF Normalization ¦ StoredProcedures | 2023-12-03 | 2023-12-03 | NA |  | Team leader divided the work among teammates
100% | Preparation (Set up GitHub for collaboration) | 2023-12-03 | 2023-12-03 | NA |  | Shared and set up github for collaboration.
100% | Reading on related material for the project. | 2023-12-03 | 2023-12-03 | NA |  | Read material online necessary for the project.
100% | Completed table normalization + Table Creation + UDT's | 2023-12-03 | 2023-12-06 | NA |  | Completed Respective Tables
100% | Complete Stored Procedures | 2023-12-03 | 2023-12-06 | NA |  | Completed Respective Stored Procedures
100% | Create directory for project files. | 2023-12-03 | 2023-12-06 | NA |  | Team leader created the directory for all the files of the project.
100% | Presentation and Recordings | 2023-12-07 | 2023-12-07 | 2023-12-08 |  | Professor Extended Deadline.
100% | Submission of VHDX File | 2023-12-07 | 2023-12-07 | 2023-12-08 |  | Professor Extended Deadline.
100% | Follow-up¦ Future assignments and delegation complete. | 2023-12-07 | 2023-12-07 | 2023-12-08 |  | Professor Extended Deadline.

## Group member 2
To-do list
To be completed by: |  | 2023-12-08 |  | Name Arnan Khan
Deadline: |  | 2023-12-08 |  | Date 12/07/2023
Project 3
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Delegate consturcting tables ¦ 3NF Normalization ¦ StoredProcedures | 2023-12-03 | 2023-12-03 | NA |  | Team leader divided the work among teammates
100% | Preparation (Set up GitHub for collaboration) | 2023-12-03 | 2023-12-03 | NA |  | Shared and set up github for collaboration.
100% | Reading on related material for the project. | 2023-12-03 | 2023-12-03 | NA |  | Read material online necessary for the project.
100% | Completed table normalization + Table Creation + UDT's | 2023-12-03 | 2023-12-06 | NA |  | Completed Respective Tables
100% | Complete Stored Procedures | 2023-12-03 | 2023-12-06 | NA |  | Completed Respective Stored Procedures
100% | Create directory for project files. | 2023-12-03 | 2023-12-06 | NA |  | Team leader created the directory for all the files of the project.
100% | Presentation and Recordings | 2023-12-07 | 2023-12-07 | 2023-12-08 |  | Professor Extended Deadline.
100% | Submission of VHDX File | 2023-12-07 | 2023-12-07 | 2023-12-08 |  | Professor Extended Deadline.
100% | Follow-up¦ Future assignments and delegation complete. | 2023-12-07 | 2023-12-07 | 2023-12-08 |  | Professor Extended Deadline.

## Group member 3
To-do list
To be completed by: |  | 2023-12-08 |  | Name Abdul Mohammed
Deadline: |  | 2023-12-08 |  | Date 12/07/2023
Project 3
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Delegate consturcting tables ¦ 3NF Normalization ¦ StoredProcedures | 2023-12-03 | 2023-12-03 | NA |  | Team leader divided the work among teammates
100% | Preparation (Set up GitHub for collaboration) | 2023-12-03 | 2023-12-03 | NA |  | Shared and set up github for collaboration.
100% | Reading on related material for the project. | 2023-12-03 | 2023-12-03 | NA |  | Read material online necessary for the project.
100% | Completed table normalization + Table Creation + UDT's | 2023-12-03 | 2023-12-06 | NA |  | Completed Respective Tables
100% | Complete Stored Procedures | 2023-12-03 | 2023-12-06 | NA |  | Completed Respective Stored Procedures
100% | Create directory for project files. | 2023-12-03 | 2023-12-06 | NA |  | Team leader created the directory for all the files of the project.
100% | Presentation and Recordings | 2023-12-07 | 2023-12-07 | 2023-12-08 |  | Professor Extended Deadline.
100% | Submission of VHDX File | 2023-12-07 | 2023-12-07 | 2023-12-08 |  | Professor Extended Deadline.
100% | Follow-up¦ Future assignments and delegation complete. | 2023-12-07 | 2023-12-07 | 2023-12-08 |  | Professor Extended Deadline.

## Group member 4
To-do list
To be completed by: |  | 2023-12-08 |  | Name Aureljo Pepa
Deadline: |  | 2023-12-08 |  | Date 12/07/2023
Project 3
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Delegate consturcting tables ¦ 3NF Normalization ¦ StoredProcedures | 2023-12-03 | 2023-12-03 | NA |  | Team leader divided the work among teammates
100% | Preparation (Set up GitHub for collaboration) | 2023-12-03 | 2023-12-03 | NA |  | Shared and set up github for collaboration.
100% | Reading on related material for the project. | 2023-12-03 | 2023-12-03 | NA |  | Read material online necessary for the project.
100% | Completed table normalization + Table Creation + UDT's | 2023-12-03 | 2023-12-06 | NA |  | Completed Respective Tables
100% | Complete Stored Procedures | 2023-12-03 | 2023-12-06 | NA |  | Completed Respective Stored Procedures
100% | Create directory for project files. | 2023-12-03 | 2023-12-06 | NA |  | Team leader created the directory for all the files of the project.
100% | Presentation and Recordings | 2023-12-07 | 2023-12-07 | 2023-12-08 |  | Professor Extended Deadline.
100% | Submission of VHDX File | 2023-12-07 | 2023-12-07 | 2023-12-08 |  | Professor Extended Deadline.
100% | Follow-up¦ Future assignments and delegation complete. | 2023-12-07 | 2023-12-07 | 2023-12-08 |  | Professor Extended Deadline.

## Group member 5
To-do list |  | FOLLOWING MEMBER DID NOT COMPLETE ANY DELIVERABLES
To be completed by: |  | 2023-12-08 |  | Name Akash Ramakaran
Deadline: |  | 2023-12-08 |  | Date 12/07/2023
Project 3
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
0% | Delegate consturcting tables ¦ 3NF Normalization ¦ StoredProcedures | 2023-12-03 | 2023-12-03 | NA |  | Team leader divided the work among teammates
0% | Preparation (Set up GitHub for collaboration) | 2023-12-03 | 2023-12-03 | NA |  | Shared and set up github for collaboration.
0% | Reading on related material for the project. | 2023-12-03 | 2023-12-03 | NA |  | Read material online necessary for the project.
0% | Completed table normalization + Table Creation + UDT's | 2023-12-03 | 2023-12-06 | NA |  | Completed Respective Tables
0% | Complete Stored Procedures | 2023-12-03 | 2023-12-06 | NA |  | Completed Respective Stored Procedures
0% | Create directory for project files. | 2023-12-03 | 2023-12-06 | NA |  | Team leader created the directory for all the files of the project.
0% | Presentation and Recordings | 2023-12-07 | 2023-12-07 | 2023-12-08 |  | Professor Extended Deadline.
0% | Submission of VHDX File | 2023-12-07 | 2023-12-07 | 2023-12-08 |  | Professor Extended Deadline.
0% | Follow-up¦ Future assignments and delegation complete. | 2023-12-07 | 2023-12-07 | 2023-12-08 |  | Professor Extended Deadline.

## Group member 6
To-do list
To be completed by: |  | 2023-12-08 |  | Name Mudabir Rizvi
Deadline: |  | 2023-12-08 |  | Date 12/07/2023
Project 3
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Delegate consturcting tables ¦ 3NF Normalization ¦ StoredProcedures | 2023-12-03 | 2023-12-03 | NA |  | Team leader divided the work among teammates
100% | Preparation (Set up GitHub for collaboration) | 2023-12-03 | 2023-12-03 | NA |  | Shared and set up github for collaboration.
100% | Reading on related material for the project. | 2023-12-03 | 2023-12-03 | NA |  | Read material online necessary for the project.
100% | Completed table normalization + Table Creation + UDT's | 2023-12-03 | 2023-12-06 | NA |  | Completed Respective Tables
100% | Complete Stored Procedures | 2023-12-03 | 2023-12-06 | NA |  | Completed Respective Stored Procedures
100% | Create directory for project files. | 2023-12-03 | 2023-12-06 | NA |  | Team leader created the directory for all the files of the project.
100% | Presentation and Recordings | 2023-12-07 | 2023-12-07 | 2023-12-08 |  | Professor Extended Deadline.
100% | Submission of VHDX File | 2023-12-07 | 2023-12-07 | 2023-12-08 |  | Professor Extended Deadline.
100% | Follow-up¦ Future assignments and delegation complete. | 2023-12-07 | 2023-12-07 | 2023-12-08 |  | Professor Extended Deadline.